Student’s code:……………….

Student’s name:………………

- Online test (30’ – 4 marks)

- Exercise:  (60’ - 6 marks)

# Ex1: (1.5 marks)

Assume that there are two projects A and B can be invested and estimated the data on the costs and benefits obtained annually according to the following table:

|  | year 1 | year 2 | year 3 | year 4 | year 5 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Project A |  |  |  |  |  |  |
| Cost |  |  |  |  |  |  |
| Benefit |  |  |  |  |  |  |
| Project B |  |  |  |  |  |  |
| Cost |  |  |  |  |  |  |
| Benefit |  |  |  |  |  |  |

# Interest rate: 10%.

# Question

# Write formulate and calculate NPV of two project:  ………….

# If a project is selected based on the net present value (NPV) then what project is selected: ………..

# Ex2 :(4.5 marks)

Currently, TOM Group is planning a project to building an IoT framework and the project management department has set up tasks for implementation as follow:

| Task | Predecessors | Duration (day) | Reduce time (day) | Cost for reduce/day |
| --- | --- | --- | --- | --- |
| A |  | 3 | 0 | - |
| B |  | 4 | 2 | 10 |
| C |  | 5 | 1 | 50 |
| D |  | 11 | 4 | 20 |
| E |  | 10 | 4 | 60 |
| F |  | 8 | 2 | 40 |
| G |  | 9 | 4 | 150 |
| H |  | 7 | 3 | 30 |
| I |  |  |  |  |

Perform the following requirements:

- Draw PERT diagrams by task and fill in the values (Duration time, ES: Earliest Start date, EF: Earliest Finish date, LS: Latest Start date, LF: Latest Finish date) of each activity.

(Example Ans.)

- Calculate duration to complete the project: 37 months

- List tasks on critical path of the project: A, B, F, I

- Shorten the execution time of the project in 7 days with cheapest cost. Determine the order of tasks to be shortened, the time is shortened on each task and then filling the following table:

| No. | Task | R. Time | Cost |
| --- | --- | --- | --- |
| 1 | I | 1 | 3 |
| 2 | A | 2 | 10 |
| 3 | F | 4 | 52 |
| 4 | E+F | 1 | 18 |
| 5 | B | 1 | 19 |
| Tổng |  |  | 102 |

- Draw GANTT diagram of project after shortening

(Example Ans.)